## SCRUM CYCLE
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 1
| 2019-11-01 | 60 | 62 |  | Laurel | 14 | 2.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 56 | 58.4 |  | Mathew | 14 | 2.8 |  | As a user I should be able to view the menu | Add Menu Appetizer items to local db | high | Done
| 2019-11-03 | 52 | 54.8 |  | Lydelle | 14 | 2.8 |  |  | Add Menu Entrees items to local db | high | Done
| 2019-11-04 | 48 | 51.2 |  | Dalton | 10 | 2 |  |  | Add Menu Desserts items to local db | high | Done
| 2019-11-05 | 44 | 47.6 |  | Jada | 10 | 2 |  |  | Add Menu Drinks items to local db | high | Done
| 2019-11-06 | 40 | 44 |  |  | 62 | 12.4 |  |  | Add functionality to view appetizers | high | Done
| 2019-11-07 |  | 40.4 | [6 empty] | Add functionality to view main courses | high | Done
| 2019-11-08 |  | 36.8 | [6 empty] | Add functionality to view desserts | high | Done
| 2019-11-09 |  | 33.2 | [6 empty] | Add functionality to view drinks Create home screen | high | Done
| 2019-11-10 |  | 29.6 | Sprint Number: 1 | [5 empty] | Add functionality to the homescreen appetizers button | high | Done
| 2019-11-11 |  | 26 |  | Start Date: | 2019-11-02 |  |  |  | Add functionality to the homescreen main course button | high | Done
| 2019-11-12 |  | 22.4 |  | End Date: | 2019-11-05 |  |  |  | Add functionality to the homescreen desserts button | high | Done
| 2019-11-13 |  | 18.8 |  | Sprint Length | 4 days |  |  |  | Add functionality to the homescreen drinks button | high | Done
| 2019-11-14 |  | 15.2 |  | Hours Per Day: | 4hrs |  |  |  | Add functionality to the homescreen call waiter button | high | Done
| 2019-11-15 |  | 11.6 | [6 empty] | Add functionality to the homescreen view bill | high | Done
| 2019-11-16 |  | 8 | [6 empty] | Add functionality to the homescreen my order button | high | Done
| 2019-11-17 |  | 4.4 | [6 empty] | Adjust the homescreen layout | high | Done
| 2019-11-18 |  | 0.8 | Sprint Number: 2
| 2019-11-19 |  | 0 |  | Start Date: | 2019-11-08
| 2019-11-20 |  | 0 |  | End Date: | 2019-11-12
[5 empty] | Sprint Length | 4 days
[5 empty] | Hours Per Day: | 4hrs
| NOTES |  |  | Sprint Number: 3
[5 empty] | Start Date: | 2019-11-15
[5 empty] | End Date: | 2019-11-17
[5 empty] | Sprint Length | 2 days
[5 empty] | Hours Per Day: | 4hrs
Sprint Number: 4
[5 empty] | Start Date: | 2019-11-18
[5 empty] | End Date: | 2019-11-20
[5 empty] | Sprint Length | 2 days
[5 empty] | Hours Per Day: | 4hrs