## SCRUM CYCLE 1
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 1
| 2019-11-01 | 60 | 62 |  | Laurel | 14 | 2.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 56 | 58.4 |  | Mathew | 14 | 2.8 |  | As a user I should be able to view the menu | Add Menu Appetizer items to local db | high | Done
| 2019-11-03 | 52 | 54.8 |  | Lydelle | 14 | 2.8 |  |  | Add Menu Entrees items to local db | high | Done
| 2019-11-04 | 48 | 51.2 |  | Dalton | 10 | 2 |  |  | Add Menu Desserts items to local db | high | Done
| 2019-11-05 | 44 | 47.6 |  | Jada | 10 | 2 |  |  | Add Menu Drinks items to local db | high | Done
| 2019-11-06 |  | 44 |  |  | 62 | 12.4 |  |  | Add functionality to view appetizers | high | Done
| 2019-11-07 |  | 40.4 | [6 empty] | Add functionality to view main courses | high | Done
| 2019-11-08 |  | 36.8 | [6 empty] | Add functionality to view desserts | high | Done
| 2019-11-09 |  | 33.2 | [6 empty] | Add functionality to view drinks Create home screen | high | Done
| 2019-11-10 |  | 29.6 | Sprint Number: 1 | [5 empty] | Add functionality to the homescreen appetizers button | high | Done
| 2019-11-11 |  | 26 |  | Start Date: | 2019-11-02 |  |  |  | Add functionality to the homescreen main course button | high | Done
| 2019-11-12 |  | 22.4 |  | End Date: | 2019-11-05 |  |  |  | Add functionality to the homescreen desserts button | high | Done
| 2019-11-13 |  | 18.8 |  | Sprint Length | 4 days |  |  |  | Add functionality to the homescreen drinks button | high | Done
| 2019-11-14 |  | 15.2 |  | Hours Per Day: | 4hrs |  |  |  | Add functionality to the homescreen call waiter button | high | Done
| 2019-11-15 |  | 11.6 | [6 empty] | Add functionality to the homescreen view bill | high | Done
| 2019-11-16 |  | 8 | [6 empty] | Add functionality to the homescreen my order button | high | Done
| 2019-11-17 |  | 4.4 | [6 empty] | Adjust the homescreen layout | med | Working
| 2019-11-18 |  | 0.8
| 2019-11-19 |  | 0
| 2019-11-20 |  | 0
NOTES

## SCRUM CYCLE 2
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 2
| 2019-11-01 | 60 | 62 |  | Laurel | 14 | 2.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 56 | 58.4 |  | Mathew | 14 | 2.8 |  | As a user I should be able to add and or delete items from my order | Database package: Setup db | high | Done
| 2019-11-03 | 52 | 54.8 |  | Lydelle | 14 | 2.8 |  |  | Database creation: (1) Connect db & (2) Create table | high | Done
| 2019-11-04 | 48 | 51.2 |  | Dalton | 10 | 2 |  |  | Database Helper: Create DB Helper | high | Done
| 2019-11-05 | 44 | 47.6 |  | Jada | 10 | 2 |  |  | Connect db to the application | high | Done
| 2019-11-06 | 40 | 44 |  |  | 62 | 12.4 |  |  | Adding a menu item to the db | high | Pending
| 2019-11-07 | 40 | 40.4 | [6 empty] | Adding multiple items to the db | high | Done
| 2019-11-08 | 40 | 36.8 | [6 empty] | Deleting a menu item from the db | high | Pending
| 2019-11-09 | 36 | 33.2 | [6 empty] | Deleting multiple items from the db | high | Done
| 2019-11-10 | 33 | 29.6 | Sprint Number: 1 | [5 empty] | Integration testing to ensure the db connect smoothly and performed as expected | low | Blocked
| 2019-11-11 | 29 | 26 |  | Start Date: | 2019-11-02 |  |  |  | User input to adjust the quantity of an item to the order | low | Working
| 2019-11-12 | 25 | 22.4 |  | End Date: | 2019-11-05 |  |  |  | Adjusting the layout of the application
| 2019-11-13 | 21 | 18.8 |  | Sprint Length | 4 days
| 2019-11-14 | 18 | 15.2 |  | Hours Per Day: | 4hrs
| 2019-11-15 | 14 | 11.6
| 2019-11-16 |  | 8
| 2019-11-17 |  | 4.4
| 2019-11-18 |  | 0.8 | Sprint Number: 2
| 2019-11-19 |  | 0 |  | Start Date: | 2019-11-08
| 2019-11-20 |  | 0 |  | End Date: | 2019-11-15
[5 empty] | Sprint Length | 7 days
[5 empty] | Hours Per Day: | 4hrs
NOTES:
Sprint 2: 3 extra day was added to the reschedule as a result of unforeseen circumstances with the extrernal db we chose to work with.
The remaing pending task would be completed in the next sprint.

## SCRUM CYCLE 3
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 3
| 2019-11-01 | 60 | 62 |  | Laurel | 14 | 2.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 56 | 58.4 |  | Mathew | 14 | 2.8 |  | As a user I should be able to View my current bill | Adding items to db from all menu screens | high | Done
| 2019-11-03 | 52 | 54.8 |  | Lydelle | 14 | 2.8 |  |  | Deleting items to db from all menu screens | high | Done
| 2019-11-04 | 48 | 51.2 |  | Dalton | 10 | 2 |  |  | User test to ensure the data shown on the bill reflect what the user selected or updated on their order. | high | Done
| 2019-11-05 | 44 | 47.6 |  | Jada | 10 | 2
| 2019-11-06 | 40 | 44 |  |  | 62 | 12.4 |  | As a user I should be able to call the waiter to my table | Generate a response when the user selects the call waiter button | med | Done
| 2019-11-07 | 40 | 40.4 | [6 empty] | Developer the time mechanism | high | Done
| 2019-11-08 | 40 | 36.8 | [6 empty] | Perform user test on the call waiter button to ensure the timer performs as expected. | med | Done
| 2019-11-09 | 36 | 33.2 | [6 empty] | Food tracker progress bar | low | Blocked
| 2019-11-10 | 33 | 29.6 | Sprint Number: 1
| 2019-11-11 | 29 | 26 |  | Start Date: | 2019-11-01
| 2019-11-12 | 25 | 22.4 |  | End Date: | 2019-11-05
| 2019-11-13 | 21 | 18.8 |  | Sprint Length | 4 days
| 2019-11-14 | 18 | 15.2 |  | Hours Per Day: | 4hrs
| 2019-11-15 | 14 | 11.6
| 2019-11-16 | 11 | 8
| 2019-11-17 | 7 | 4.4
| 2019-11-18 | 4 | 0.8 | Sprint Number: 2
| 2019-11-19 | 1 | 0 |  | Start Date: | 2019-11-09
| 2019-11-20 | 0 | 0 |  | End Date: | 2019-11-15
[5 empty] | Sprint Length | 7 days
[5 empty] | Hours Per Day: | 4hrs
Sprint Number: 3
[5 empty] | Start Date: | 2019-11-16
[5 empty] | End Date: | 2019-11-19
[5 empty] | Sprint Length | 3 days
[5 empty] | Hours Per Day: | 4hrs
NOTES:
Sprint 3: 1 extra day was added to the reschudle as two task were remained uncompleted at the end of sprint 2.