## SPRINT CYCLE 1
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 1
| 2019-11-01 | 80 | 82 |  | Laurel | 19 | 3.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 76 | 78.8 |  | Mathew | 18 | 3.6 |  | As a user I should be able to view the menu | Add Menu Appetizer items to local db | high | Done
| 2019-11-03 | 72 | 75.2 |  | Lydelle | 14 | 2.8 |  |  | Add Menu Entrees items to local db | high | Done
| 2019-11-04 | 68 | 71.6 |  | Dalton | 14 | 2.8 |  |  | Add Menu Desserts items to local db | high | Done
| 2019-11-05 | 64 | 68 |  | Jada | 15 | 3 |  |  | Add Menu Drinks items to local db | high | Done
| 2019-11-06 |  | 64.4 |  |  | 80 | 16 |  |  | Add functionality to view appetizers | high | Done
| 2019-11-07 |  | 60.8 | [6 empty] | Add functionality to view main courses | high | Done
| 2019-11-08 |  | 57.2 | [6 empty] | Add functionality to view desserts | high | Done
| 2019-11-09 |  | 53.6 | [6 empty] | Add functionality to view drinks Create home screen | high | Done
| 2019-11-10 |  | 50 | Sprint Number: 1 | [5 empty] | Add functionality to the homescreen appetizers button | high | Done
| 2019-11-11 |  | 46.4 |  | Start Date: | 2019-11-02 |  |  |  | Add functionality to the homescreen main course button | high | Done
| 2019-11-12 |  | 42.8 |  | End Date: | 2019-11-05 |  |  |  | Add functionality to the homescreen desserts button | high | Done
| 2019-11-13 |  | 39.2 |  | Sprint Length | 4 days |  |  |  | Add functionality to the homescreen drinks button | high | Done
| 2019-11-14 |  | 35.6 |  | Hours Per Day: | 4hrs |  |  |  | Add functionality to the homescreen call waiter button | high | Done
| 2019-11-15 |  | 32 | [6 empty] | Add functionality to the homescreen view bill | high | Done
| 2019-11-16 |  | 28.4 | [6 empty] | Add functionality to the homescreen my order button | high | Done
| 2019-11-17 |  | 24.8 | [6 empty] | Adjust the homescreen layout | med | Working
| 2019-11-18 |  | 21.2
| 2019-11-19 |  | 17.6
| 2019-11-20 |  | 14
| 2019-11-21 |  | 10.4
| 2019-11-22 |  | 6.8
| 2019-11-23 |  | 3.2
| 2019-11-24 |  | 0
| 2019-11-25 |  | 0
| 2019-11-26 |  | 0
| 2019-11-27 |  | 0
| 2019-11-28 |  | 0
| 2019-11-29 |  | 0
NOTES:

## SPRINT CYCLE 2
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 2
| 2019-11-01 | 80 | 82 |  | Laurel | 19 | 3.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 76 | 78.8 |  | Mathew | 18 | 3.6 |  | As a user I should be able to add and or delete items from my order | Database package: Setup db | high | Done
| 2019-11-03 | 72 | 75.2 |  | Lydelle | 14 | 2.8 |  |  | Database creation: (1) Connect db & (2) Create table | high | Done
| 2019-11-04 | 68 | 71.6 |  | Dalton | 14 | 2.8 |  |  | Database Helper: Create DB Helper | high | Done
| 2019-11-05 | 64 | 68 |  | Jada | 15 | 3 |  |  | Connect db to the application | high | Done
| 2019-11-06 | 60 | 64.4 |  |  | 80 | 16 |  |  | Adding a menu item to the db | high | Done
| 2019-11-07 | 60 | 60.8 | [6 empty] | Adding multiple items to the db | high | Pending
| 2019-11-08 | 60 | 57.2 | [6 empty] | Deleting a menu item from the db | high | Done
| 2019-11-09 | 56 | 53.6 | [6 empty] | Deleting multiple items from the db | high | Pending
| 2019-11-10 | 52 | 50 | Sprint Number: 1 | [5 empty] | Integration testing to ensure the db connect smoothly and performed as expected | high | Done
| 2019-11-11 | 48 | 46.4 |  | Start Date: | 2019-11-02 |  |  |  | User input to adjust the quantity of an item to the order | low | Done
| 2019-11-12 | 44 | 42.8 |  | End Date: | 2019-11-05 |  |  |  | Adjusting the layout of the application | med | Working
| 2019-11-13 | 40 | 39.2 |  | Sprint Length | 4 days
| 2019-11-14 | 36 | 35.6 |  | Hours Per Day: | 4hrs
| 2019-11-15 | 32 | 32
| 2019-11-16 |  | 28.4
| 2019-11-17 |  | 24.8
| 2019-11-18 |  | 21.2 | Sprint Number: 2
| 2019-11-19 |  | 17.6 |  | Start Date: | 2019-11-08
| 2019-11-20 |  | 14 |  | End Date: | 2019-11-15
| 2019-11-21 |  | 10.4 |  | Sprint Length | 7 days
| 2019-11-22 |  | 6.8 |  | Hours Per Day: | 4hrs
| 2019-11-23 |  | 3.2
| 2019-11-24 |  | 0
| 2019-11-25 |  | 0
| 2019-11-26 |  | 0
| 2019-11-27 |  | 0
| 2019-11-28 |  | 0
| 2019-11-29 |  | 0
NOTES:
Sprint 2: 3 extra day was added to the reschedule as a result of unforeseen circumstances with the extrernal db we chose to work with.
The remaing pending task would be completed in the next sprint.

## SPRINT CYCLE 3
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 3
| 2019-11-01 | 80 | 82 |  | Laurel | 19 | 3.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 76 | 78.8 |  | Mathew | 18 | 3.6 |  | As a user I should be able to View my current bill | Adding items to db from all menu screens | high | Done
| 2019-11-03 | 72 | 75.2 |  | Lydelle | 14 | 2.8 |  |  | Deleting items to db from all menu screens | high | Done
| 2019-11-04 | 68 | 71.6 |  | Dalton | 14 | 2.8 |  |  | User test to ensure the data shown on the bill reflect what the user selected or updated on their order. | high | Done
| 2019-11-05 | 64 | 68 |  | Jada | 15 | 3
| 2019-11-06 | 60 | 64.4 |  |  | 80 | 16 |  | As a user I should be able to call the waiter to my table | Generate a response when the user selects the call waiter button | med | Done
| 2019-11-07 | 60 | 60.8 | [6 empty] | Developer the time mechanism | high | Done
| 2019-11-08 | 60 | 57.2 | [6 empty] | Perform user test on the call waiter button to ensure the timer performs as expected. | high | Done
| 2019-11-09 | 56 | 53.6 | [6 empty] | Food tracker progress bar | low | Blocked
| 2019-11-10 | 52 | 50 | Sprint Number: 1
| 2019-11-11 | 48 | 46.4 |  | Start Date: | 2019-11-01
| 2019-11-12 | 44 | 42.8 |  | End Date: | 2019-11-05
| 2019-11-13 | 40 | 39.2 |  | Sprint Length | 4 days
| 2019-11-14 | 36 | 35.6 |  | Hours Per Day: | 4hrs
| 2019-11-15 | 32 | 32
| 2019-11-16 | 30 | 28.4
| 2019-11-17 | 26 | 24.8
| 2019-11-18 | 22 | 21.2 | Sprint Number: 2
| 2019-11-19 | 16 | 17.6 |  | Start Date: | 2019-11-09
| 2019-11-20 |  | 14 |  | End Date: | 2019-11-15
| 2019-11-21 |  | 10.4 |  | Sprint Length | 7 days
| 2019-11-22 |  | 6.8 |  | Hours Per Day: | 4hrs
| 2019-11-23 |  | 3.2
| 2019-11-24 |  | 0
| 2019-11-25 |  | 0
| 2019-11-26 |  | 0 | Sprint Number: 3
| 2019-11-27 |  | 0 |  | Start Date: | 2019-11-16
| 2019-11-28 |  | 0 |  | End Date: | 2019-11-19
| 2019-11-29 |  | 0 |  | Sprint Length | 3 days
[5 empty] | Hours Per Day: | 4hrs
NOTES:
Sprint 3: 1 extra day was added to the reschudle as two task were remained uncompleted at the end of sprint 2.
At our sprint meeting we decided to mot implement the food tracking function.

## SPRINT CYCLE 4
S C R U M P L A N N I N G
| DATE | HOURS LEFT | ESTIMATE | Group Members |  | Hrs in Total | 12hrs wk | S P R I N T # 3
| 2019-11-01 | 80 | 82 |  | Laurel | 19 | 3.8 | USER STORIES |  | TASKS | PRIORITY | STATUS
| 2019-11-02 | 76 | 78.8 |  | Mathew | 18 | 3.6 |  | Revisiting: As a user I should be able to view the app. | Created a start up slash image | low | Done
| 2019-11-03 | 72 | 75.2 |  | Lydelle | 14 | 2.8 |  |  | Adjusted the layout from grid to list | high | Done
| 2019-11-04 | 68 | 71.6 |  | Dalton | 14 | 2.8 |  |  | Formatted the all screens for consistency | high | Done
| 2019-11-05 | 64 | 68 |  | Jada | 15 | 3 |  |  | Added a colour scheme to the application and sub screens | med | Done
| 2019-11-06 | 60 | 64.4 |  |  | 80 | 16 |  |  | Added familiar icons for the user to recognise the menu sections | med | Done
| 2019-11-07 | 60 | 60.8 | [6 empty] | Adjusted the design of all buttons | med | Done
| 2019-11-08 | 60 | 57.2 | [6 empty] | Perform system testing to ensure all functionality was operational after the upgrade on look | high | Done
| 2019-11-09 | 56 | 53.6
| 2019-11-10 | 52 | 50 | Sprint Number: 1
| 2019-11-11 | 48 | 46.4 |  | Start Date: | 2019-11-01
| 2019-11-12 | 44 | 42.8 |  | End Date: | 2019-11-05
| 2019-11-13 | 40 | 39.2 |  | Sprint Length | 4 days
| 2019-11-14 | 36 | 35.6 |  | Hours Per Day: | 4hrs
| 2019-11-15 | 32 | 32
| 2019-11-16 | 30 | 28.4
| 2019-11-17 | 26 | 24.8
| 2019-11-18 | 22 | 21.2 | Sprint Number: 2
| 2019-11-19 | 16 | 17.6 |  | Start Date: | 2019-11-09
| 2019-11-20 | 12 | 14 |  | End Date: | 2019-11-15
| 2019-11-21 | 12 | 10.4 |  | Sprint Length | 7 days
| 2019-11-22 | 12 | 6.8 |  | Hours Per Day: | 4hrs
| 2019-11-23 | 8 | 3.2
| 2019-11-24 | 5 | 0
| 2019-11-25 | 0 | 0
| 2019-11-26 | 0 | 0 | Sprint Number: 3
| 2019-11-27 | 0 | 0 |  | Start Date: | 2019-11-16
| 2019-11-28 | 0 | 0 |  | End Date: | 2019-11-19
| 2019-11-29 | 0 | 0 |  | Sprint Length | 3 days
[5 empty] | Hours Per Day: | 4hrs
Sprint Number: 4
[5 empty] | Start Date: | 2019-11-22
[5 empty] | End Date: | 2019-11-25
[5 empty] | Sprint Length | 4 days
[5 empty] | Hours Per Day: | 4hrs
NOTES:
Sprint 3: 1 extra day was added to the reschudle as two task were remained uncompleted at the end of sprint 2.